## Slide 1
TRAVEL
WP3 - EVALUATION TOOLKIT
E R A S M U S + P R O J E C T
N . 2 0 2 3 - 1 - I T 0 2 - K A 2 2 0 - S C H - 0 0 0 1 5 4 1 7 3
TRAINING ROADMAPS TO ACCESS VIRTUAL ENVIRONMENTAL LEARNING
II TRANSNATIONAL PROJECT MEETING
4-5 DECEMBER 2024
Kaunas - Lithuania
BETI
ANTARES SRL

## Slide 2
OBJECTIVES
Objective: Provide teachers with tools for a comprehensive assessment of students' preparation in sustainable development and environmental education.
Features:
Integrated assessment across four dimensions: skills, knowledge, values, attitudes/behaviors.
Focus: Measure the assimilation of environmental topics and introduce Green Skills into the educational offerings of upper secondary schools, with priority given to technical and scientific programs.

## Slide 3
MAIN RESULTS
Outcome: Evaluation Toolkit to measure four dimensions of environmental education
  Skills: Green Skills and Multiliteracy Skills related to thematic content and educational processes.
  Knowledge: Environmental knowledge integrated with STEM subjects (e.g., geology, chemistry, computer science).
  Attitudes/Behaviors: Focused on protecting and enhancing the environment.
  Values: Aligned with environmental sustainability.
Key Reference: The European GreenComp Framework (2022), defines competencies and approaches across four areas:
Sustainability values, Complexity in sustainability
Sustainable futures, Acting for sustainability
Tools: Questionnaires, tests, observation grids, interviews
Support: Guide Manual for administration and scoring

## Slide 4
ACTIVITIES and TIMING
Activity 1 | Development of Assessment Tools | 01/01/2025 - 12/05/2025
Activity 2 | Training on the Evaluation Toolkit | 13/05/2025 - 29/08/2025

## Slide 5
TASK AND RESPONSABILITIES
ANTARES is the leading partner of WP3
In detail:
1. Development of Assessment Tools
  ANTARES is responsible for creating the Evaluation Toolkit.
    Initial phase: Literature review to identify relevant tools, indicators, and models, shared and discussed with school partners.
    Responsibilities of IS partners:
      Each school develops one of the four Toolkit dimensions (skills, knowledge, values, attitudes/behaviors).
      Selection of the most suitable tools is done collaboratively with ANTARES.
      School partners create evaluation tools for teachers, with close collaboration from ANTARES.
    Quality control: ANTARES integrates all tools into a single cohesive Toolkit.
    Support:
      BETI assists in the digitalization of tools.
      INDEPCIE and ARID review the clarity and coherence of items with the constructs being assessed.

## Slide 6
TASK AND RESPONSABILITIES
2. Training on the Evaluation Toolkit
  ANTARES organizes a 4-hours webinar for School teachers covering:
    Assessed dimensions.
    Designed tools.
    Implementation and result interpretation
  Webinar roles:
    School teachers present the content for their assigned dimensions.
    ANTARES designs educational materials (slides, tutorials, etc.).

## Slide 7
TASK AND RESPONSABILITIES
3. Development of the Toolkit User Manual
  ANTARES leads the drafting of the User Manual.
  INDEPCIE, ARID, and BETI support ANTARES in this process.
      Each School develops one of the four Toolkit dimensions (skills, knowledge, values, attitudes/behaviors).
      Selection of the most suitable tools is done collaboratively with ANTARES.
      School partners create evaluation tools for teachers, with close collaboration
      with ANTARES.
    Quality control: ANTARES integrates all tools into a single cohesive Toolkit.

## Slide 8
ACTIVITIES IN DETAIL
1. Development of Evaluation Tools
  Goal: Create assessment tools for the 4 dimensions (skills, knowledge, values, attitudes/behaviors).
    Steps:
    a) Scientific literature review: Research on tools/indicators for evaluating sustainability and environmental awareness in youth.
    b) Online focus groups: Collaboration between IS schools and ANTARES to identify the most suitable tools/indicators.
    c) Tool development:
      Skills: Multiliteracy skills for sustainability using the Multiliteracies Map Framework (Hill, 2005).
      Knowledge: Environmental education in STEM subjects, adapting existing tests (e.g., UNESCO SDG4 indicator 4.7.5 cognitive items, 2020).
      Values: Adaptation of the Two Major Environmental Values model (2MEV; Bogner & Wiseman, 2006) assessing Preservation (P) and Utilization (U).
      Attitudes/Behaviors: Use of tools like Inclusion of Nature in the Self (INS; Schultz, 2001) or the Connectedness to Nature Scale (CNS; Mayer & Frantz, 2004).
      Framework: Tool development guided by the GreenComp model.

## Slide 9
ACTIVITIES IN DETAIL
2. Training on the Evaluation Toolkit
  Format: A 4-hour webinar for teachers.
  Structure:
    Module 1 (2 hours): Presentation of dimensions, constructs, and tools.
    Module 2 (2 hours): Guidelines for administering tools and interpreting results.
Each teacher will present the content related to their assigned dimension. At the end of the webinar, a User Manual will be drafted.

## Slide 10
ACTIVITIES & OUTPUT
1. Development of Evaluation Tools
OUTPUT: Evaluation Toolkit
Includes finalized tools for the 4 dimensions.
Contains:
Bibliographic references.
Guidelines for result interpretation.
2. Training on the Evaluation Toolkit
OUTPUT: User Manual
Details:
Assessed dimensions and constructs.
Guidelines for administering tools, data analysis, result interpretation, and feedback delivery

## Slide 11
The products will be translated into the available languages: IT, SP, LT, PL, EN

## Slide 12
PARTICIPANTS
Teachers Involvement
  Activity 1:
    Participants: 20 teachers (approximately 5 for each school) previously selected during WP Activity 3.
    Profile: As defined in WP2.
  Activity 2:
    School principals (Directors) of partner school will involve:
      Teachers who participated in previous Project-Works.
      Additional teachers of technical-scientific subjects.
    Participants: Minimum of 32 teachers in total (approximately 8 for school partner).

## Slide 13
INDICATORS AND EVALUATION TOOLS
Quantitative:
  4.7.1, sub-indicator "D - Student Assessment" (pre/post comparison):
    D2: Number and type of sustainability-related topics included in student assessments.
    D3: Number and type of sustainability dimensions (knowledge, skills, attitudes, values) included in student assessments.
  Tools: Online questionnaire based on UNESCO items (SDG 4.7.1, 12.8.1, 13.3.1 document).
Qualitative:
  Methodology: Plenary meetings with teachers and semi-structured interviews.
    Goals:
      Application of the Toolkit beyond Virtual Field Trips (e.g., curricular assessments in technical-scientific subjects).
      Analysis of the Toolkit’s usability and effectiveness (strengths and areas for improvement).
Quality Evaluation
  Tools:
    Likert Scale (1-5) to assess tools (clarity, coherence, exhaustiveness; threshold ≥3/5).
    Training Satisfaction Rating Scale (min. 80% participants satisfied).
    YES/NO Checklist for the Final Manual (clarity, coherence, exhaustiveness).

## Slide 14
Funded by the European Union. Views and opinions expressed are however those of the author(s) only and do not necessarily reflect those of the European Union or the European Education and Culture Executive Agency (EACEA). Neither the European Union nor EACEA can be held responsible for them.